# WRP Procurement ToolKit – Quick Start

Part of Weather Ready Pacific Standard, Optimisation & Maintenance Guidelines Document

This Quick Start Guide will get you ready to develop your tender making clear what documents you can consider given your role and responsibilities.

## Which Document Do I Need?

## The 10-Step Procurement Process

| Step | Activity | Time Needed | Key Document | Who Leads |
| --- | --- | --- | --- | --- |
| 1 | Define your need | 1-2 weeks | Tier Selection Guide (p.XX) | Technical Manager |
|  | ☐What variables must be measured? |  |  |  |
|  | ☐ Which tier (1/2/3) do you need? |  |  |  |
|  | ☐ How many stations/systems? |  |  |  |
|  | ☐ Where will they be located? |  |  |  |
| 2 | Check budget | 1 week | Lifecycle Cost Worksheet | Finance Officer |
|  | ☐ Capital available? |  |  |  |
|  | ☐ Operations budget confirmed? |  |  |  |
|  | ☐ Spare parts funded? |  |  |  |
| 3 | Draft specifications | 1-2 weeks | System Module Templates | Technical + Procurement |
|  | ☐ Select your system type |  |  |  |
|  | ☐ Copy the tier specifications |  |  |  |
|  | ☐ Add site-specific requirements |  |  |  |
| 4 | Prepare tender documents | 1 week | RFT Master Template | Procurement |
|  | ☐ Complete all sections |  |  |  |
|  | ☐ Attach specs as Annex |  |  |  |
|  | ☐ Get legal review |  |  |  |
| 5 | Release and manage queries | 4-6 weeks | Query Log Template | Procurement |
|  | ☐ Advertise (min 30 days) |  |  |  |
|  | ☐ Respond to all questions |  |  |  |
|  | ☐ Issue clarifications |  |  |  |
| 6 | Receive and register bids | 1 day | Bid Register | Procurement |
|  | ☐ Check deadlines |  |  |  |
|  | ☐ Log all submissions |  |  |  |
|  | ☐ Initial compliance check |  |  |  |
| 7 | Evaluate technical bids | 2-3 weeks | Evaluation Scorecard | Technical Panel |
|  | ☐ Score each criterion |  |  |  |
|  | ☐ Minimum 70% technical score |  |  |  |
|  | ☐ Shortlist |  |  |  |
| 8 | Evaluate financial bids | 1 week | TCO Calculator | Finance + Procurement |
|  | ☐ Check for unrealistically low bids |  |  |  |
|  | ☐ Calculate weighted score |  |  |  |
|  | ☐ Prepare recommendation |  |  |  |
| 9 | Award contract | 1-2 weeks | Contract Template | Legal + Procurement |
|  | ☐ Negotiate if needed |  |  |  |
|  | ☐ Obtain bank guarantee |  |  |  |
|  | ☐ Sign contract |  |  |  |
| 10 | Manage delivery | Per contract | Lifecycle Management Tools | Technical Manager |
|  | ☐ Oversee installation |  |  |  |
|  | ☐ Ensure training delivered |  |  |  |
|  | ☐ Track warranty & spares |  |  |  |

## Quick Help

| For help with... | Contact | When |
| --- | --- | --- |
| Technical specifications | [Your NMHS technical lead] | During steps 1-3 |
| Procurement process | [Your procurement officer] | Throughout |
| Regional coordination | SPREP WRP Team | For pooled procurement |
| Calibration questions | WMO Regional Instrument Centre | Before specifying |
| Training support | RTC Nadi / RTC Melbourne / SPREP WRP Team | During planning |

## Quick Tips

Avoid making these mistakes:

Buying equipment without operations budget → Use Lifecycle Cost Worksheet

Specifying Tier 1 when you need Tier 2 → Check the tier guide carefully

Not including training in contract → Training is mandatory (Section 4.5)

Single point of failure in communications → Always require redundant telemetry

Ignoring corrosion protection → Pacific requirements are non-negotiable

## Next Steps

Now that you understand the process, proceed to:

For PROCUREMENT STAFF: Go to [Procurement Toolkit - Part A: Master Templates]

For TECHNICAL STAFF: Go to [Procurement Toolkit - Part B: System Modules]

For BOTH: Review [Checklists] before starting any step