## Slide 1: WRP Implementation Plan and Funded Work Plan Update V2.1
Weather Ready Pacific Steering Committee 4
2 June 2026

## Slide 2: Decision sought from SC
WRP has made updates to the implementation plan and funded work plan to 2029. No activities have been changed and no new activities or projects have been added since the last approved version 2.0 from SC3.
This is a minor update to reflect:
  Budget adjustments following underspend in 2025 which is reallocated to future years.
  Re-forecasting timing of future activities and associated budget allocations.
  Latest forecasted cost to complete activities and projects (i.e. Samoa Radar)
All proposed changes since last approved Work Plan is documented in the Adaptations & Change Register (Annex 1) for transparency.
SC4 Dec 6.1.1 - The SC approves the updated WRP Implementation Plan and funded Work Plan 2024 to 2029 v2.1

## Slide 3: Change Register Record
Activity No. | Activity Name | Work Plan Funding New (USD '000) | Work Plan Funding Previous (USD '000) | Proposed Adaptation/ Changes (detail the proposed adaptation/change required, including what, how, who and when to achieve a more successful outcome)
1.1.1 | Establish the PMU, Operational Processes and WRP pooled fund | 339 | 356 | Unused funds from 2025 redistributed. Communication strategy done in-house so $50k funding was reallocated. Including additional $27k funds allocated to Branding and Advertising to support implementation of communication strategy. Corrections in actual budgets from ESNZ cause of the main decrease.
1.1.2 | Operational Phase of PMU and coordination activities | 2,596 | 2,622 | Unused funds from 2025 redistributed. Addtiional $112k funding allocated to WRP SC and Liaison Platform to cover expected costs. $45k added to staff start up costs.
1.1.3 | MERL framework establishment and operationalisation | 153 | 133 | MFAT provided additional $20k in 2026 towards MERL implemenation.
1.1.4 | PMU Staff (Management and Delivery Support roles) | 4,404 | 4,725 | Savings made as a result of delayed/deferred recruitment. PMU roles are budgeted higher which acts as a contingency for the program - unused funds from 2025 redistributed.
1.2.1 | Sustainable hydrometeorological financing investment facility | 100 | 0 | Allocation of $100k funding to start investigation on a financing facility (if world bank is not able to provide TA support).
1.3.1 | GEDSI and social safeguards mainstreamed into WRP | 292 | 221 | Additional $71k budget allocated to support mainstreaming GEDSI into WRP implementation from 2026 out to 2029. This is to help cover disability accomodations in events and workshops venues per feedback from DFAT in IDS.
4.1.1 | Develop an Integrated Forecasting Platform and strengthen RSMCs (incl WIS, CAP) | 1,757 | 2,557 | $800k funds originally provisioned for 2028 has been reallocated to Samoa radar in order to fully fund the radar activities in 2026 and 2027 (SC approved out-of-session). Required for IFP in future will be determined as the IFP design is completed and ICT gaps confirmed.
4.2.1 | Strengthen aviation forecasting | 30 | 30 | 
4.2.2 | Strengthen public forecasting | 598 | 598 | 
4.2.3 | Strengthen marine forecasting | 0 | 0 | 
4.2.4 | Strengthen coastal inundation forecasting | 1,205 | 1,191 | Minor budget adjustments to cover cost of Lidar surveys for Marshall Islands.
4.2.5 | Strengthen hydrological services and riverine flood forecasting | 93 | 93 | 
4.2.6 | Provide additional ICT and other technical staff to expand capacity | 910 | 1,067 | Budget savings/reduction due to delayed recruitment by countries on ICT staff.

## Slide 4: Change Register Record
3.1.1 | Implement observation network plans, asset management, standardised infrastructure, data management and maintenance practices | 917 | 977 | $100k fund reallocated from here to 1.3.1 sustainable financing investment facility (in the event that World Bank is not able to provide TA support). Re-forecasted expenditure for 2026 to 2027 for development of asset plans, network plans and asset information system. $20k budget allocated towards development of Geohazard network asset plan/strategy.
3.1.2 | Provide asset management and maintenance staff to expand capacity (e.g. SPREP, SPC, NMHS) | 1,078 | 1,074 | Minor budget adjustments for rounding.
3.1.5 | Establish weather watch radars | 8,312 | 6,962 | Increased budget by $1350k to cover cost of the Samoa radar in 2027 capital cost.
2.1.1 | Establish and operate a Regional Training Centre (RTC) | 224 | 238 | Minor budget adjustments to reflect actual cost of regional workshop and business model review for RTC and RIC.
2.2.2 | Training on specialised forecasting services, and assessment of competencies (e.g. marine, aviation, hydrology/ hydrography) | 110 | 160 | Cost of Hydrologist training (BIP-H) in Pagasa lower than forecasted. Budget reduction by $50k.
2.2.3 | Training of observers, technicians and ICT specialists, and assessment of competencies | 272 | 296 | Unused funds from 2025 redistributed. Cost of BIP MT training $24k lower than forecasted.
2.2.5 | Specialised regional workshops and training courses | 164 | 207 | Unused funds from 2025 redistributed. Cost of CAP training $43k lower than forecasted.
2.2.6 | Provide additional staff for training and capacity development | 714 | 742 | Budget savings/reduction due to delayed recruitment of PMU Training and Capacity Development Advisor.
0 | Contingency and Other | 612 | 700 | Underspend by countries Readiness Fund/Flexi-fund in 2025 has been reallocated. Resulting in overall reduction in funding by $138k.
0 | GRAND TOTAL (excl. SPREP program fees) | 28,460 | 28,612 | Minor increase in total committed funding from MFAT to cover consultant cost for MERL implementation in 2026. Corrections in actual budgets from ESNZ cause of main decrease.
Activity No. | Activity Name | Work Plan Funding New (USD '000) | Work Plan Funding Previous (USD '000) | Proposed Adaptation/ Changes (detail the proposed adaptation/change required, including what, how, who and when to achieve a more successful outcome)

## Slide 5: Decision sought from SC
SC4 Dec 6.1.1 - The SC approves the updated WRP Implementation Plan and funded Work Plan 2024 to 2029 v2.1