Annex 2. WRP Delegations Authority

Version History

| Date | Version | Author/Revisor |
| --- | --- | --- |
| 20 May 2025 | 1 | Second WRPP Steering Committee Meeting in Honiara |
| 26 Sep 2025 | 2 | Third WRPP Steering Committee Meeting in Honiara |
| 2 June 2026 | 3 | Fourth WRPP Steering Committee Meeting in Honiara |

|  | Ministers/SPREP Council/PIF | PMC | Steering Committee | SPREP/WRP |
| --- | --- | --- | --- | --- |
| Governance & Funding | Approval of new funding mechanism for SPREP/WRP. E.g. WRP pooled funding or investment facility Approval of new regional initiatives that require high level country consent. | PMC has responsibility for strategic policy relating to WRP. This includes without limitation: Approval of beneficiaries of WRP. Approval of changes to Steering Committee membership. Approval of changes to the governance of WRP. Power to instigate a strategic review of WRP (including its priorities). Approval of ‘major’ changes to the Delegations Policy (i.e. changes that require amendment to the PMC Terms of Reference) | The SC has responsibility for supervising the management of WRP, including without limitation: Approval of annual work plans and budgets, and validation of progress reports. Review of PMU performance including compliance with MERL indicators. Approval of Delegations Policy within the framework of the PMC and SC ToR. Providing regular reports to the PMC on program performance and policy issues requiring strategic guidance from the PMC. Approval of the establishment, closure or alternation of the WRP Pooled Fund; Approval of new WRP Donors; Approval of new WRP Donor contributions, approval of any new funding mechanism or financing structure; Approval of material reallocation of staff-cost contingency or budget buffer within the approved annual planning process; | Approval and signing of grant/donor funding agreements and MOUs to deliver WRP implementation plan – limits of authority per SPREP financial delegations Approval of any departure from standard programme-management-fee or cost-recovery treatment. Maintain WRP audit plan and schedule |

| Delivery | Decision on changes to and/or extend scope of Accountabilities & Responsibilities in SPREP, WRP and NMHSs in their legislation and agreement/charters | Approval of WRP investment plan and costings, including any subsequent revisions or requests for additions. Approval of strategic regional/national policies and plans impacting meteorological services, developed by WRP but without limiting: - Network plans and strategies - Asset, technology, ICT and data standards/architecture - Asset and data management - Regional functions governance and operating model (e.g. RTC, RIC) | Approval of implementation plan and budget, including annual updates and changes requests from PMC Out of session approvals to changes in implementation planning or budgets. Monitoring of Programme progress, learnings, evaluating the effectiveness of interventions, and recommending adaptations as necessary to achieve Programme goals. Identification of potential risks to Programme implementation and recommend risk mitigation strategies. Decision to assist a Member who is undergoing a State of Emergency where the activity is not a WRP Implementation activity but is within the PMC approved WRP Investment Plan. Approval of material changes to the Operations Manual | Approval of expenditure per the implementation plan activity if within allocated budget +30% or +$70k- limits of authority per SPREP. Decisions on work sequencing and phasing within implementation plan activity, if within allocated budget +30% or +$70k Decisions to defer or bring forward activities by more than 1 year to be raised with steering committee for noting only. Approval of expenditure not yet in work plan but within investment plan objective and meets MERL outcomes - up to USD200k limit. These will be raised with Steering committee for noting and reflected in annual implementation plan and work plan updates. Decisions on procurement approach and delivery partners Continual updates to and approval of Operations Manual |
| --- | --- | --- | --- | --- |

| Reporting |  |  | Approval of the WRP Reporting Framework, including any amendment to the WRP Reporting Framework, any supplementary WRP Donor reporting incorporated into the WRP Reporting Framework, and any assurance or compliance report prepared for the WRP Donors. Approval of MERL framework and any subsequent changes Approval of annual report for publication. | Approval of routine progress reporting against implementation plan to steering committee, PMC, donors and technical committee. |
| --- | --- | --- | --- | --- |
| Staffing |  |  | Out of session approvals to changes in budget in implementation plan Approval of staffing where above implementation plan budget more than +30% | Decisions on SPREP staffing plan, recruitment and associated costs to deliver on WRP implementation plan provided it is within budget +30%. Changes to staffing plan to be raised with steering committee and PMC for noting only. |
| MHEW Readiness fund (flexi-fund) |  |  | Out of session approvals to changes in budget in implementation plan. | Approval of request from individual countries, to spend against the national capacity readiness fund – up to USD20k limit per request, provided the approved budget has not been exceeded and complies with the WRP request process. |