## Slide 1: Lessons Learned – FY2025 What WRP Learned – and What It Did About It
A Steering Committee 4 Presentation
1-2 June 2026
Honiara, Solomon Islands

## Slide 2: Purpose
To present WRP's FY2025 lessons learned for Steering Committee notation, acceptance and endorsement - demonstrating that WRP is a programme that builds on its own evidence
(See Lessons Learned section of the FY2025 Annual Report – page 65)

## Slide 3
LESSONS LEARNED — FY2025
What WRP Learned — and What It Did About It
Presented to the Steering Committee — June 2026
These lessons were drawn from WRP's first full year of implementation and consolidated in the FY2025 Annual Report. We are presenting them in June 2026 — which means many have already been acted on. This deck is structured to reflect that: where action has been taken, we ask the SC to note and close.
ALREADY ADDRESSED
Action taken since FY2025. SC to note and close.
IN PROGRESS
Underway in 2026. SC to note and monitor.
WRP doesn't just learn — it acts. The lessons below are evidence of adaptive management in practice.
Weather Ready Pacific | FY2025 Lessons Learned | Overview

## Slide 4
STRATEGIC LESSONS — WHERE THINGS STAND IN JUNE 2026
Four lessons · All have been acted on
Addressed
Country engagement must precede major governance decisions
IFP country consultation process was redesigned after SC3 non-approval. Individual country engagement is now a precondition built into the IFP Phase 2 timeline. SC to note and close.
In progress
Donor expenditure targets must be paced to stakeholder readiness
PMU has raised adaptive disbursement milestones in donor dialogue. Discussions with DFAT and MFAT ongoing. Language for future agreements being drafted. SC to note and monitor.
The PFIF (Pooled Fund Investment Facility) is the programme's single most urgent structural priority
Paper is already being tabled for SC4 for deliberation and approval - Agenda Item 9.1 – Operationalisation of the WRP Pooled Fund. SC to note and monitor.
In progress
Currency exchange rate variances are generating invisible financial losses
PMU has identified the scope of the issue. A treasury management approach is being developed. SC to note and monitor
Weather Ready Pacific | FY2025 Lessons Learned | Strategic Lessons — Status
In progress

## Slide 5
MANAGERIAL & OPERATIONAL LESSONS — STATUS AS AT JUNE 2026
Most are already being actioned. SC asked to note.
SC papers require an adequate preparation runway.
Now in SC planning calendar. Met Directors closed session added to SC agenda template.
In progress
Key-person dependency creates bottlenecks and knowledge loss.
Shared documentation and task distribution underway. Understudy arrangements being formalised in 2026.
Addressed
The BoM–SPREP MOU model should be replicated.
Broad-scope EA agreement model adopted. Being applied to all new executing agency arrangements.
In progress
MERL data collection must be continuous.
Data quality check-ins added to Technical Committee agenda.
Addressed
SPREP December–January closure creates 6 weeks of procurement downtime.
October procurement initiation deadline embedded in 2026 annual planning calendar.
Addressed
Radar procurement should be split across specialist providers.
Split procurement model embedded in Samoa radar specs and now standard for all WRP radar installations.
Addressed
Continuous user feedback loops improve tool quality.
Pulse survey and validation interview model from Severe Weather Pilot now standard for all WRP technology deployments.
In progress
IFP and observation network data flows must be co-scoped.
Joint scoping session requirement added to IFP Phase 2 design process. First session scheduled.
In progress
In-country training generates demand for extended engagement.
Budget contingency for extended in-country delivery being built into 2026–27 training programme designs.
In progress
BIP-M/MT graduates return to software not available at home.
Pre-return software assessments and transition support being designed into all training programmes from 2026.
Weather Ready Pacific | FY2025 Lessons Learned | Managerial & Operational Lessons
In progress

## Slide 6
STEERING COMMITTEE PROPOSED RESOLUTION
Lessons Learned — FY2025
NOTE
That WRP's first full year of implementation has generated a substantive body of learning across strategic, managerial and operational domains — and that the programme has already acted on all lessons identified.
ACCEPT/ ENDORSE
The managerial and operational lessons as reported, the PMU's 2026 actions in response, and the status updates presented — noting that lessons rated 'Addressed' are closed, and those rated 'In Progress' will be reported at SC on an ongoing basis.
Weather Ready Pacific | FY2025 Lessons Learned | SC Resolution

## Slide 7: Any insights from Steering Committee, EAs and Donors that would complement or add on to what has been shared today?
Tank yu tumas
Open Discussion